## Sheet1
RAI Conversion to XML Rough Steps
What | Help
Design
Setup P&G Side Development Environment with Target Site Loaded | Amabel
Connect RAID Emulator to Server
Provide Specification to Vendor
Review Specification with Vendor
Provide BamBam Emulator to Vendor
RTCIS Only - Analyze Special Use Cases for Specific Site - Stacked Pallets etc
RTCIS/RAID Test Special Use Cases
RAID Modifications Needed? | Fortech
Test RAID Modifications
Confirm basic communication test (Heartbeat) between Vendor System and BAMBAM
Agree on testing protocol / develop test plans for next phase
Development Testing - Technical Users
Setup New RTCIS Server Specifically for Testing | Project
Load Target Site into Test Server | L2
Connect RAID to Test Server and Confirm Basic Operation
Basic connectivity test - Single Heartbeat Exchange
Burn in heartbeat test (24-48 hours of rapid heartbeat exchange)
E2E System testing
SIT Testing
User driven testing with testing servers used in previous phase
Setup processes to be used in BAT for "Weekend" testing and how to resync all systems at end of testing
BAT Testing
Upgrade Production System to RTCIS version | L2
Identify necessary bug patches and apply | L2/Amabel
Connect RAID to test3 and confirm basic operations
Test the physical production equipment with test environments of RTCIS and Vendor systems
Setup processes to be used to revert to RAI in Production if necessary and how to resync all systems
Production
Startup test the physical production equipment with live environments of RTCIS and Vendor systems
Go Live Support