## Sheet1
ID | Emulator Testing | Status | Fix Ver | Comment
1 | test sending the A20 as right now the A20 can be sent from SAP via RTCIS, or there is aIso a command we can do from RTCIS to cancel an order, which causes an A20 to ASRS. We use this when we want to cancel an order and pull out ulids, or cancel an order and de-stage it (U21, D23,D24). | Retest | Bam 0.8 | Sending Functionality Built into BamBAm
2 | A20 Processing in RAID | Retest | 0.2 | Send A24 after receipt of A20
3 | A26 testing - tried to send 5 ulids in a shipment so I could send an A26 and make sure it only staged one more, but BAMBAM would always default to 2 ulids for shipment, | Toni | NA | Change bambam line items ini Setting from 2 to 5?
4 | When A24 is sent from RAID the A32 was automatically sent. Didn't expect the A32 to be auto sent, as right now it's just sent if slot signon is sent or if someone signs onto truckoading, | Retest | Bam 0.8 | Added BAMBAM ini control parameter to control AutoSend
5 | Sent A13 with a blank location and didn't get a location back - was thinking the RAID 13S would have the location filled in if the 13R was blank, | Toni | NA | We may need to look at this together, worked ok for me
6 | Sent manual output request for 5 ulids and would expect a slot back, similar to 4 in that it was blank | Toni | NA | The sending of Msg13 vs MSg21 is controlled on RTCIS side. So for now RAID will accept Msg13s with ULID qtys >3
7 | Sent msg 13 for a specific ulid (LNK0009) and got an error that said the specified UL does not exist (when it was in cust_pallet). | Retest | 0.2 | For ulid wthdrw created CUST_SHIPMENT to be consistent, also fixed retro_status on cust_pall to be 14 after stage
8 | Msg 13 activ_output location says 9 and I sent a request for 2 ulids to 91 but msg13 response from RAID did come back with a 91 (just chopping off the second digit in display). | Toni | NA | We may need to look at this together, worked ok for me
9 | In Access db, for ulids that have manually been requested out the RETRO_LOC stays at ASRS instead of 91, 92, etc. The location did update for a shipment (1A, 1B) | Retest | 0.2
10 | APP_DATE shows YYYYMMDD for date for shipments , but correct for manual withdrawals. | Retest | 0.2 | Already had fixed - also resized display columns
11 | Unstage Message Capability (U21, D23, D24) | Retest | 0.3
12 | BamBam Msg21 Configuration Capability | Retest | Bam 0.9
13
14
15
16
17
18
19
20
21
22
23
24
25
26